VERMONT SOUTH BOWLS CLUB ACTION PLAN 2025 - 2027

This action plan has been created in July 2025 and will be reviewed quarterly.

Created: 30/7/25

Reviewed: February 2026

Reviewed:

This action plan identifies the ways we can continue to keep the bowls section:

- Viable/Sustainable/Thriving

- High profile and successful

- Moving forward together as a club

- A great place to belong.

| Focus area: GOVERNANCE |  |  |  |  |
| --- | --- | --- | --- | --- |
| GOAL: Up to date rules, policies and procedures Objective: To align our rules, policies and procedures to the National Integrity Framework overseen by Sport Integrity Australia |  |  |  |  |
| Actions/Activities | Person responsible for progressing (Resources and support) | Time line | Measure of success | Result/Progress |
| - Review and update VSBC rules - Develop and implement a Code of Conduct policy - Review and update duty descriptions for all roles - Completion of the Club Health Check on Bowls Aus/Clubmap website - Develop a calendar of events for circulation to committee members for each meeting and for publishing to members - A list of work projects is developed for the bowls section and presented to the VSC for consideration and progressing as part of the future planning VSC project | Bowls Committee (Bowls Vic; Bowls Australia; Clubmap) Mike Petty Bowls Committee Greens Director Catering Manager | To be finalised by 2026 AGM Immediate After VSC AGM in Sept | All rules, policies and procedures are up to date, adopted and understood by members of the bowls section Committee members have a clear picture of our commitments for the upcoming year Bowls section’s work priorities are included in future planning projects at VSC level | Review of draft rules has been completed. To be presented for adoption at the 2026 AGM Code of conduct policy finalised, published and on bowls noticeboard Duty descriptions for all roles completed Health check and results completed for consideration in 2026 new action plan. In place and ongoing A list of work projects for the bowls section submitted to VSC Sept’25 |
| Focus area: COMMUNICATION, PROMOTION AND MARKETING |  |  |  |  |
| GOAL: Efficient and Effective Communication that is transparent, open and honest/keeping everyone informed Objective: Underpins everything we do, builds relationships, keeps people involved and informed, brings in new members |  |  |  |  |
| Actions/Activities | Person responsible for progressing (Resources and support) | Time line | Measure of success | Result/Progress |
| - Social Media - explore opportunities to reach out to communities and attract new members. - Regularly publishing news, information and social events on our Facebook page. Linking in to other relevant bowls Facebook pages - VSC Website to have the bowls section updated or rewritten so it becomes a resource for club members and the community - Handbook or yearly planner to be developed for bowls members. - Barefoot bowls flyer to be developed in Chinese and circulated into the Chinese community to encourage attendance on Friday nights. Flyer to be sent to Probus groups - Maintain current communication with members via ENews, weekly running sheets and committee contacts/minutes | Pam Janssen Leanne Bourke Website Sub-committee Jim Cull Dean Stubley Mike Petty Committee members | Immediate and ongoing | Members satisfaction with communication within and external to the club Responses and contact eventuating from Facebook posts Website is attracting interest and new members Our handbook remains a resource for our members We gain new members from the Chinese community. We gain new members from other avenues Our members are informed | Social media team in place and actions to be presented to new 2026 committee Opportunities are identified and published/ongoing Sub-committee of Mike Petty, Peter Morgan, Steve Raymond and Roy Arscott progressing Completed and distributed to members Updated flyers have been created for TRY bowls season; as handouts for corporate barefoot bowls sessions and for letterbox drop. Exploring flyer in different languages In place and ongoing |
| Focus area: SOCIAL FABRIC; CULTURE and WELLBEING |  |  |  |  |
| GOAL: Inclusive and supportive approach to all members/we support each other /Maintain a proactive approach to the culture of our club and the wellbeing of our members Objective: Every member knows WE CARE |  |  |  |  |
| Actions/Activities | Person responsible for progressing (Resources and support) | Time line | Measure of success | Result/Progress |
| - Maintain regular social functions - Drive a recruitment strategy through Fridays Barefoot bowls and corporate barefoot bowls bookings - Develop a checklist of the stages of learning for a new member which improves their integration into the club - Develop a Wellbeing/Vale Policy - Review list of current members - First aid kits to be checked 6 monthly and Defib training to be organised - Organise and tidy the greenhouse for members to use. Make sure the main function room is kept tidy. - New member “welcome and brief profile” to be placed in Enews when membership is approved | Social Committee Mike Petty, Ken George, Committee members Bowls Committee Coaches New member officers Dean Stubley Rhona Bastiani Graeme Durrant (Enews) Bowls Committee Dean Stubley /Rhona Bastiani Health & Safety Sub-committee Appointed bowls members/coaches Bowls Chairperson | Ongoing Every Friday Immediate Immediate 1 month Every 6 months Ongoing Ongoing | Culture of social enjoyment and a sense of belonging Increase in membership Members feeling welcome and involved in the club Policy provides a consistent understanding and approach for all members Committee has a better understanding of members activities Kits and Defib training is up to date and readily available for members to use Greenhouse is fit for purpose Members feel welcome | Social committee develops schedule of events ongoing Try/Barefoot bowls flyer to be handed out to every corporate barefoot bowls event/jack attack etc VSC Community Day has now been scheduled for 26/4/26 Completed and implemented Completed and implemented Completed and being monitored by wellbeing officers – Rhona Bastiani and Dean Stubley 11 First Aid Officers in place, OH&S sub-committee led by Paul Bastiani (Craig Anderson, Pam Barnhill and Dean Stubley) now up and running, regular checking schedule in progress Defib training completed. Completed and ongoing Implemented and ongoing |
| Focus area: TOURNAMENTS/SOCIAL BOWLS |  |  |  |  |
| GOAL: Maximising participation, skill level and building relationships Objective; Maximum member participation |  |  |  |  |
| Actions/Activities | Person responsible for progressing (Resources and support) | Time line | Measure of success | Result/Progress |
| - Review and develop a schedule for Club Championships for 2025/26 including rules and encourage members to nominate - Planning and running our annual Tournaments: - Balmoral Cup - Super 4s - Ladies Day - Running of the inaugural Club Challenge - Create a committee contact for the Social Bowls Program and create social program. Update flyer - Run the Mega Bowl Day on Melbourne Cup Day | Graeme D Mal Walker David Fisher John Strybosch Mike Petty Di Agius Di Agius/Sue Morgan Croydon Bowls Club Peter Morgan Social convenors Peter Morgan Mike Petty | Sept’25 As scheduled Oct’25 Immediate Nov’25 | Increase in members entering the club championships Championships viewed as a success We receive a full list of entries and we continue the history of success We receive maximum entries from both clubs and the players view the day as a success Social program is running well and convenors feel connected to the committee Everyone involved views the day as a success | Completed and Championships are in progress Balmoral Cup scheduled for April 2026 Super 4s scheduled for April 19/2026 Ladies Day scheduled for March 28/2026 Completed successfully Completed and new data sheet to be implemented Completed successfully |  |
| Focus area: PENNANT/Coaching and Skills Development |  |  |  |  |
| GOAL: Maximise participation of members in the competitive arm of the Bowls Club/ To be successful and competitive Objective: maximise the potential skills within the club involved in competition |  |  |  |  |
| Actions/Activities | Person responsible for progressing (Resources and support) | Time line | Measure of success | Result/Progress |
| - Appoint a playing Head Coach - Coaches/Selectors and Bowls Committee forum to determine goals and strategies for the upcoming season including a mid-season review - Player’s performance assessment process to be reviewed - Club Catchcry for Pennant to be explored with members | Di Agius/Bowls Committee Di Agius/Bowls Committee John Strybosch Di Agius/Bowls Committee Members | Aug 25 Sept 25 Sept 25 Sept 25 | Head Coach appointed and implementing a coaching program for all players Goals and strategies are developed and communicated to all players Players understand the assessment process and completing ratings every week Pennant players determine whether we have a catchcry for the season | Completed and in progress Completed Sept’25 Completed and new assessment process implemented Club Catchcry introduced “Go Vees”, signage installed and continuing reinforcement/encouragement ongoing |
| Focus area: VOLUNTEERS (Office Bearers; Committee/Sub-Committees; Catering; Housekeeping/Other |  |  |  |  |
| GOAL: Maximising involvement of members in the running of the club/Recognising our volunteers and their hard work Objective: Viable club; We are all in this together |  |  |  |  |
| Actions/Activities | Person responsible for progressing (Resources and support) | Time line | Measure of success | Result/Progress |
| - Continually identify and drive the need for volunteer involvement in running the club - Roving reporter role be undertaken to raise awareness of the different roles and responsibilities of all volunteer groups, recognising the contribution they make. Provide knowledge around what they do and opportunities for members to become more involved in their club. - Thank you and recognition forums acknowledging our volunteers will be included at each AGM. - Bowls presentation will be combined with the AGM each year - Local Legend award will be presented at each AGM | Bowls Committee All members Steve Raymond Bowls Committee Bowls Committee Bowls Committee | Ongoing AGM AGM AGM AGM | Everyone is involved in the activities required to run the bowls section Volunteers feel valued and acknowledged. More members contributing to the running of the club Volunteers feel valued and acknowledged Maximising attendance of members and a sense of belonging Members appreciate the level of recognition | Spotlight articles in Enews to encourage volunteer involvement. Continual encouragement for AGM vacancies. Steve Raymond has completed 3 roles published in Enews. Ongoing Implemented and ongoing at each AGM with an afternoon tea and Local legend award recognising volunteers also Implemented and ongoing Implemented and ongoing |